## Slide 1: Phase One Proposed Pre June Plan
Future Accommodation Change Management

## Slide 2: The Challenge
The Information Technology Directorate (ITD) is reorganising its workspace at Eveleigh.
The Department’s new strategy, to put the child at the center of our decision making and the teacher at the focus of our delivery, has prompted us to commence working on a Digital Strategy to align our work towards it.
This means that our work has begun to change and now involves more collaboration between teams, as well as corporate and teaching staff temporarily joining various teams in different combinations.
It’s necessary to change our accommodation to match.
We have planned some changes in the Information Technology Directorate environment and are sharing them in a consultative and informed way, in order to meet the challenge in a way that causes the least disruption and maximum benefit to our staff.

## Slide 3: The Solutions
With Eveleigh being an existing building it is recommended to modify the current assets and work practices in some ways to accommodate the challenges we face.
Using the work practices at the 105 Phillip Street Parramatta Office (‘105P’) as an influence, the Eveleigh Office have designed some modifications for the Future Accommodation Strategy in two ways:
Assets
    Providing staff with lockers for secure storage of personal items and work items
    Reducing team and personal storage with supported clean up activities
    Updating meeting rooms with new equipment, new paint and white boards
    Introducing collaborative furniture to help teams work flexibly
    Lowering partitions to create a more connected working environment
Work Practices
    Embracing DoE Flexible Working Arrangements Policy
    Practicing Paper-Lite and clean desk practices
    Strengthening shared workplace practices such as desk sharing and ‘hot desking’

## Slide 4: The Roadmap
Support and review
Project team to check in with each floor and review the space and outstanding requirements
Commence “Leading in an Agile Environment” Training for Leaders
Finalise and confirm scope with Executives
Meet with the PSA
Engage Change Champions
Set up ABW Experience Centre
Communicate to staff on the next 8 week activities and next steps (storage clean up and Experience Centre)
Experience Center live all week
Executives briefed on the clean up activities
Further communication distributed to staff about clean up activities
Week starting
13 May
Week starting
20 May
Week starting
27 May
Week starting
3 June
Week starting
10 June
*Flexible Working is inclusive of Clean Desk, Paper-Lite and Flexible Working Policy
How we are sequencing activities
Week starting
17 June
Week starting
24 June
Week starting
1 July
Week starting
8 July
Week starting
15 July
Week starting
22 July
Level 10
Staff invited to work flexibly
Level 8
Staff invited to work flexibly
Kitchens restocked with crockery, cutlery and appliances
Communication distributed to staff about about lockers, tubs and working flexibly
Training on principles and practices of ABW
Lockers installed and allocated
Unused Tambour units removed from floors
Partitions lowered
Training on principles and practices of ABW
Communication distributed to staff about about working flexibly
Refresh to meeting rooms
Training on principles and practices of ABW
Communication distributed to staff about about working flexibly
Clean up week 2
Kitchen deep clean
Storage tubs for lockers issued to people across all floors
Secure bins, Document Storage, general bins and a place to return unused hardware
Clean up week 1
Secure bins, Document Storage, general bins and a place to return unused hardware
Level 11
Staff invited to work flexibly

## Slide 5: The Process
Continued consultation with our staff at the ITD Eveleigh to understand how best to address the challenges we face.
Liaison with the Department’s Industrial Relations (IR) and Health and Safety (HS) Directorates to understand and mitigate any issues or risk involved with the proposed changes.
Presentation of a project plan to the ITD Executive and endorsement.
Regular communication to staff with activities and timelines.
Evaluation of changes made and reassessment where this is considered necessary.

## Slide 6: The Benefits
The results that we are aiming for include:
Creating capacity for our future requirements under the Digital Strategy.
Providing staff with flexible seating options as required by work demands.
Reconsidering the way we use our existing and future capacity to maximise benefit to staff, and changing our work environment to suit this.
Leveraging the advantages of a changed work environment to introduce new work practices that help our staff to continue to be safe and efficient.
Maintaining a workspace at ITD that is safe, productive and attractive to staff.

## Slide 7: Support
The results that we are aiming for include:
Dedicated Change Manager allocated to the Future Accommodation Strategy.
Access to H&S Directorates to understand and mitigate any issues or risks.
Employee Assistance Program support.
Training provided for all staff at ITD on the principles and practices of activity based working.
Training provided for leaders at ITD on leading in a flexible environment.

## Slide 8: The Summary
We are reorganising our workspace in a way that minimises disruption and uses the change to make improvements to our environment.
Since the requirement for change is necessary, we have decided to make improvements to our environment which include refreshing some of our assets, embracing DoE Flexible Working Arrangements Policy, practicing Paper-Lite and clean desk practices and strengthening shared workplace practices such as desk sharing or ‘hot desking.’
The improvements follow the principles used successfully at 105P and provide excellent guidance for what would work best at ITD.
Human Resources and HS are available to provide an expert assurance service regarding our plans and making sure that they comply with legislation and appropriate work practices.
The next steps will be to begin communicating with ITD Executives, Change Champions and staff on the activities that will occur over the coming weeks.